## Sheet2
Weekly Milestone Report
Strategic Priority | Activity | Owner | Date Due | Status | Details/Outcome/Help Needed
Example:
Product launch | Product specifications agreed | Beth | 2006-01-28 | on target | should be 1 week early
| Equipment ordered | Charlie | 2006-02-28 | tracking | OK IF product specs on time
| Materials ordered | David | 2006-02-28 | tracking | OK IF product specs on time
| Package design agreed | Fred | 2006-02-28 | lagging | Research running two weeks late
| Equipment delivered | Charlie | 2006-04-28 | tracking | OK IF product specs on time
| Plant tooling complete | Hal | 2006-05-24 | tracking | OK IF product specs on time
| Materials delivered | David | 2006-05-31 | tracking | OK IF product specs on time
| Packaging delivered to plant | Fred | 2006-05-31 | lagging | will be late if packaging not ordered on time
| Product manufactured | Jerry | 2006-06-01 | lagging | will be late if packaging not delivered on time
| 1st Ship | Jerry | 2006-06-01 | lagging | will be late if manufacturing delayed
Process: |  |  |  | on target
Prior to meeting: |  |  |  | tracking
- Each team member submits their updates |  |  |  | lagging
- Updates compiled and circulated prior to the meeting
At meeting:
This process is about anticipating milestones at risk and then adjusting as a team to make most critical ones, letting others slip as appropriate
1st half of meeting | Each team member gives five minute update during the first half of the meeting
- most important wins
- most important learnings
- areas they need help on
Pause to prioritize | Leader orders topics for discussion in priority order at half way point
2nd half of meeting | Group discusses those topics in that order during second half of meeting, spending as much time as necessary on each one
Remaining topics deferred to next meeting or separate meeting